## Slide 1
Lamphun Smart Green Mobility
Phase 1 and Phase 2 Delivery Timeline
Phase 1 focuses on public launch readiness by 30 September 2026. Phase 2 adds customer, tourism, connected-fleet, dashboard, API, and optimization enhancements through March 2027.
Operating principle
Operation First
App Ready
No Single Point of Failure
Phase timeline deck / 01

## Slide 2
Lamphun Smart Green Mobility
Two-phase delivery at a glance
Phase 1 - Must-have launch MVP
29 June-30 September 2026
Deliver the operational platform required to run 100 e-bikes with staff workflows, payment references, maintenance controls, reports, carbon estimates, and tested backup workflows.
Phase 2 - Enhancements + scale
1 October 2026-31 March 2027
Use live operating data to improve customer experience, integrate connected fleet data, expand tourism programs, build deeper dashboards, and introduce optimization support.
Gate between phases: Phase 2 should start only after rental, return, payment, maintenance, battery, incident, report, and fallback workflows are stable in live use.
Phase timeline deck / 02

## Slide 3
Lamphun Smart Green Mobility
Phase 1 delivery timeline
Must-have features to launch real operations by 30 September 2026.
Weeks 1-2
Discovery + model lock
Confirm station workflows, user roles, data model, report definitions, fallback forms, launch KPIs, and acceptance criteria.
Weeks 3-5
Core platform build
Build customer, fleet, rental, payment reference, staff permissions, and database foundations.
Weeks 6-7
Operations modules
Build maintenance, battery, incident, spare parts, QR labels, evidence capture, and fallback workflow links.
Weeks 8-9
Dashboard + reports
Build daily/monthly reports, dashboard MVP, carbon estimate, revenue reconciliation, exports, and audit views.
Weeks 10-11
Pilot + readiness
Run station pilot, train administrators and technicians, test outage scenarios, and reconcile fallback records.
Weeks 12-13
Launch hardening
Fix pilot defects, complete security and data checks, finalize SOPs, freeze launch scope, and prepare go-live support.
Phase timeline deck / 03

## Slide 4
Lamphun Smart Green Mobility
Phase 1 feature breakdown
These workstreams define the MVP scope. The common acceptance test is operational traceability: every rental, payment, asset, incident, maintenance, and fallback action must be reviewable.
Rental operations
Customer, fleet, QR asset control, check-out/check-in, battery state, photos, damage reports.
Financial traceability
Thai QR / PromptPay, card/cash references, receipts, status verification, daily reconciliation.
Asset reliability
Battery ID, charging-room record, PM schedule, work orders, repair history, spare parts usage.
Governance
Staff permissions, incident records, exports, audit trail, daily and monthly reports.
Carbon reporting
Distance accumulation, conservative carbon estimate, daily/monthly/yearly report exports.
Continuity workflow
Google Forms, Sheets, Drive evidence, and manual QR payment log for outage scenarios.
Phase timeline deck / 04

## Slide 5
Lamphun Smart Green Mobility
Phase 2 delivery timeline
Enhancements follow live evidence, API readiness, and staff capacity.
Oct-Nov 2026
Customer app enhancements
Self-service booking, route map, notifications, rental reminders, feedback, and UX improvements.
Nov-Dec 2026
Tourism promotion
Green Passport, digital stamps, hotel voucher flow, partner routes, QR check-in, and route completion badges.
Dec-Jan 2027
Connected fleet
GPS, trip history, smart lock or IoT, geofence alerts, and battery monitoring where vendor APIs are ready.
Jan-Feb 2027
Reliability analytics
Maintenance alerts, repeat failure reports, technician performance, battery health, and rotation optimization.
Feb-Mar 2027
Dashboards + APIs
Executive, operations, fleet, financial, tourism, carbon, smart-city dashboards, and partner / IoT / payment APIs.
Mar 2027 onward
Optimization layer
Demand forecast, fleet rebalancing recommendation, predictive maintenance, dynamic staffing, and tourism recommendation.
Phase timeline deck / 05

## Slide 6
Lamphun Smart Green Mobility
Phase 2 enhancement tracks
Tourism layer
Green Passport, Green Stay, partner routes, QR check-ins, vouchers, and route badges.
Connected fleet
GPS, smart lock, IoT, geofence, vehicle status, and battery monitoring integrations.
Dashboard suite
Executive, operations, fleet, maintenance, financial, tourism, carbon, and mobility dashboards.
Optimization
Demand forecast, rebalancing, predictive maintenance, battery rotation, and dynamic staffing.
Critical control: do not add GPS, IoT, AI, carbon claims, or public dashboards until the Phase 1 dataset is complete enough to support reliable decisions.
Phase timeline deck / 06

## Slide 7
Lamphun Smart Green Mobility
Decision gates and launch readiness
01
Launch MVP
All 100 e-bikes and batteries registered; staff can run rental, return, payment reference, maintenance, battery, incident, and reports.
02
Continuity proven
Backup Google Forms, Sheets, Drive evidence, and manual QR payment record are tested through an outage simulation.
03
Phase 2 start
Data completeness, workflow stability, staff readiness, and vendor API access are confirmed.
04
Scale + optimize
Dashboards are used in real decisions; carbon claims are evidence-based; connected fleet data improves operations.
The timeline is intentionally phased: stabilize operations first, then add richer customer, tourism, connected-fleet, and analytics layers.
Phase timeline deck / 07